## Sheet1
Planned | Tasks | 30/12 | 31/12 | 01/01 | 02/01 | 03/01 | 06/01 | 07/01 | 08/01 | 09/01 | 10/01 | 11/01
5 | Implement initial building functionality: houses and basic infrastructure | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 0 | Duration | Burndown
3 | Set up resource gathering basics for wood and stone | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 10 | 2
1 | Code rudimentary financial tracking | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
3 | Create a system for changing seasons (just visually) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0
3 | Set up placeholder advisors for trade and defense. | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
3 | Implement basic terrain and city layout | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Design initial assets for Viking-themed houses and resource indicators | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
2 | Add a looping Viking-inspired background track as a placeholder | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Configure project in Unity with essential packages for 3D modeling | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Set up initial building selection UI with a mouse-based placemen | 6 | 6 | 6 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0
7 | Design a non-grid-based placement system with visual feedback for selected items | 7 | 7 | 6 | 6 | 6 | 5 | 4 | 2 | 0 | 0 | 0
3 | Implement bottom status bar for resource tracking and season indicator | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40
| Total Actual | 40 | 34 | 30 | 27 | 25 | 23 | 21 | 18 | 9 | 8 | 0
| Daily Guideline | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0